## Start
Project Tracker Template | Instructions
Use this Project Tracker to manage and monitor the progress of your ongoing projects. The template helps track estimated versus actual timelines, workloads, and any variations in duration or effort. It also calculates when a project is over or under 25% of the estimated values and highlights key differences. | 1. Project Details: For each project, fill out the following: Project Name: Name of the project or task. Category: Define the project category (e.g., marketing, development). Assigned to: The name of the employee responsible for the project. 2. Estimated Values: Input the estimated start date, finish date, estimated work (in hours), and estimated duration (in days). 3. Actual Values: Once the project begins, input the actual start date, finish date, actual work completed (in hours), and actual duration (in days). 4. Tracking Over/Under: The Notes section can be used to document any reasons for deviations from the estimated values. The template will highlight where the actual work or duration exceeds or falls short of 25% from the estimates.

## Project tracker
Project Tracker |  |  |  | Percent over/under to highlighted numbers | 25%
Project | Category | Assigned to | Estimated start | Estimated finish | Estimated work (in hours) | Estimated duration (in days) | Actual start | Actual finish | Actual work (in hours) | Actual duration (in days) | Notes
Project 1 | Category 1 | Employee 1 | 2024-08-10 | 2024-10-09 | 210 | 59 | 2024-08-10 | 2024-10-14 | 300 | 64
Project 2 | Category 2 | Employee 4 | 2024-09-03 | 2024-10-04 | 400 | 31 | 2024-09-03 | 2024-10-07 | 390 | 34
Project 3 | Category 1 | Employee 2 | 2024-07-06 | 2024-09-04 | 500 | 58 | 2024-07-06 | 2024-09-17 | 500 | 71
SETUP

## Setup
Setup
Category Name | Employee Name
Category 1 | Employee 1
Category 2 | Employee 2
Category 3 | Employee 3
Category 4 | Employee 4
Category 5 | Employee 5
Category 6 | Employee 6
PROJECTS